## Sprint Planning
Sprint planning - Project Initjaion and market analysis | [8 empty] | Availbilties | [7 empty] | Total no of days
[9 empty] | Name | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun
Sprint | Issue Type | Task | Issue description | Assign to | Status | Actual Efforts | Estimated Efforts | Comments | Anuj | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5
1 |  | Conduct Stakeholder Interviews | Preparation | Anuj | done |  | 4 |  | Nikita | [7 empty] | 0
|  | Conduct Stakeholder Interviews | Interviews | Raki | done |  | 8 |  | Priscila | [7 empty] | 0
|  | Conduct Stakeholder Interviews | Analysis and Documentation | Priscila | done |  | 3 |  | Dhruvil | [7 empty] | 0
|  | Identify Problems | Gathering Information | Anuj | done |  | 3
|  | Identify Problems | Analysis | Raki | done |  | 3
|  | Identify Problems | Documentation | Priscila | done |  | 2
|  | Review Feedback on Existing Systems | Data Collection | Anuj | done |  | 3
|  | Review Feedback on Existing Systems | Qualitative Analysis | Raki | done |  | 4
|  | Review Feedback on Existing Systems | Summarizing Findings | Nikita | done |  | 3
|  | Document Functional Gaps | Comparative Analysis | Anuj | done |  | 4
|  | Document Functional Gaps | Identifying Gaps | Raki | done |  | 4
|  | Document Functional Gaps | Reporting | Priscila | done |  | 4
|  | Outline Impact on Stakeholders | Drafting Impact Descriptions | Nikita | done |  | 3
|  | Outline Impact on Stakeholders | Review and Refinement | Nikita | done |  | 2
|  | Competitive Analysis | Researching Competitors | Anuj | done |  | 8
|  | Competitive Analysis | Feature Comparison | Raki | done |  | 6
|  | Competitive Analysis | Pricing Model Analysis | Priscila | done |  | 4
|  | Competitive Analysis | Reporting | Anuj | done |  | 2
|  | Market Trends Analysis | Researching Trends | Raki | done |  | 4
|  | Market Trends Analysis | Analysis | Priscila | done |  | 2
|  | Market Trends Analysis | Documentation | Nikita | done |  | 2
|  | SWOT Analysis | Brainstorming Session | Anuj | done |  | 3
|  | SWOT Analysis | Drafting SWOT | Raki | done |  | 5
|  | SWOT Analysis | Review and Finalization | Priscila | done |  | 4
|  | Regulatory Requirements Review | Researching Regulations | Anuj | done |  | 3
|  | Regulatory Requirements Review | Summarizing Requirements | Raki | done |  | 2
|  | Regulatory Requirements Review | Implications for VMS | Priscila | done |  | 1
|  | Potential Market Segmentation | Market Data Analysis | Anuj | done |  | 3
|  | Potential Market Segmentation | Segment Identification | Raki | done |  | 2
|  | Potential Market Segmentation | Documenting Segmentation | Nikita | done |  | 2
|  | Determine Market Needs | Identifying Unmet Needs | Anuj | done |  | 3
|  | Determine Market Needs | Aligning VMS Features | Raki | done |  | 2
|  | Determine Market Needs | Finalizing Market Needs Document | Nikita | done |  | 2
Sprint Deliverables
Comments : Based on the availabilities we can plan a weekly meeting for a project
Sprint planning - Project Initjaion and market analysis
Sprint | Issue Type | Task | Issue description | Assign to | Status | Actual Efforts | Estimated Efforts | Comments
2 |  | Project Kickoff | Attend a project kickoff meeting | Priscila | done |  | 4
|  | Market Research | Conduct market research for the software solution | Anuj | done |  | 8
|  | User Needs Documentation | Identify and document user needs and requirements | Raki | done |  | 3
|  | Competitive Analysis | Begin a competitive analysis of the market | Nikita | done |  | 3
|  | Framework Outlining | Outline the basic framework for the software | Priscila | done |  | 3
|  | Feature Listing | Create a list of key features for development | Anuj | done |  | 2
|  | Project Management Research | Research project management tools and methodologies | Raki | done |  | 3
|  | Setup Project Workspace | Set up a project management workspace | Nikita | done |  | 4
|  | Risk Assessment Drafting | Draft an initial risk assessment | Priscila | done |  | 3
|  | Technology Plan Outlining | Outline a plan for technology and tool acquisition | Anuj | done |  | 4
|  | Preliminary Budget Breakdown | Prepare a preliminary budget breakdown | Raki | done |  | 4
|  | Human Resource Assessment | Assess human resource needs based on project scope | Nikita | done |  | 4